## 📊 Project Gantt
ERP PT Quty Karunia 2026-2027 — Project Gantt & Roadmap
Phase | Module / Feature | Est. Sessions | Start | End | Status | Progress % | Notes
Phase 1 | PHASE 1 — FOUNDATION |  |  |  | ✅ DONE | 100% | Completed ~Session 30 | 📅 Project Start | January 2026
1 | Authentication & RBAC | Login, JWT, Role & Permission system | 2026-01-01 | 2026-01-31 | ✅ Done | 100% | All 11 roles, fine-grained permissions | 📍 Current Date | March 2, 2026
1 | Database Schema | PostgreSQL, SQLAlchemy ORM, Base models | 2026-01-01 | 2026-01-20 | ✅ Done | 100% | Auto-migrate on startup | 🔢 Sessions Done | 51+
1 | Purchasing Module | PO KAIN / LABEL / ACC, Dual Trigger, multi-batch | 2026-01-15 | 2026-02-10 | ✅ Done | 100% | 2 MO auto-created per PO KAIN | 🎯 Target Launch | January 2027
1 | Warehouse | Material receipt, stock, FG, stock opname | 2026-01-20 | 2026-02-15 | ✅ Done | 100% | FIFO, lot tracking | 👨‍💻 Developer | Solo (Daniel Rizaldy)
1 | BOM (Dual) | BOM Production + BOM Purchasing, import from Excel | 2026-01-25 | 2026-02-05 | ✅ Done | 100% | 5845 BOM lines imported | 🏭 Client | PT Quty Karunia
Phase 2 | PHASE 2 — CORE MODULES |  |  |  | 🔵 In Progress | 45% | Current focus
2 | PPIC — MO & WO | MO BUYER/PRODUCTION, WO per dept, SPK auto | 2026-02-01 | 2026-03-15 | 🔵 In Progress | 65% | Dual MO, WO auto-creation on PO send
2 | Production Floor | Cutting/Emb/Sewing/Finishing/Packing input pages | 2026-02-10 | 2026-03-30 | 🔵 In Progress | 40% | Daily Input per dept, permission-gated
2 | BOM Management UI | Admin CRUD page for BOM headers & lines | 2026-02-20 | 2026-03-05 | ✅ Done | 100% | Session 51+
2 | Masterdata CRUD | Products, Categories, Suppliers admin pages | 2026-02-20 | 2026-03-05 | ✅ Done | 100% | Session 51+
2 | PO Delete/Approval | Request delete workflow, approval by atasan | 2026-02-25 | 2026-03-02 | ✅ Done | 100% | Session 51+
2 | Quality Control | QC Inspection, Lab Test, Rework workflow | 2026-03-01 | 2026-03-31 | ⏳ Todo | 5% | QC checkpoint, defect categories
Phase 3 | PHASE 3 — OPERATIONS |  |  |  | ⏳ Todo | 0% | Est. April–June 2026
3 | Material Debt System | Negative inventory, settlement, auto-track | 2026-04-01 | 2026-04-20 | ⏳ Todo | 0%
3 | WIP Tracking | WIP Dashboard, inter-dept transfer, buffer | 2026-04-10 | 2026-05-10 | ⏳ Todo | 0%
3 | Kanban Board | Real-time Kanban for production floor | 2026-05-01 | 2026-05-20 | ⏳ Todo | 0%
3 | Finish Goods | FG stock, dispatch, customer delivery | 2026-05-15 | 2026-06-10 | ⏳ Todo | 0%
3 | Material Allocation (SPK) | Auto-allocate materials from WH to SPK | 2026-05-20 | 2026-06-15 | ⏳ Todo | 0%
Phase 4 | PHASE 4 — REPORTING & ANALYTICS |  |  |  | ⏳ Todo | 0% | Est. July–Sept 2026
4 | Dashboard Analytics | KPI cards, real-time charts, trend analysis | 2026-07-01 | 2026-07-31 | ⏳ Todo | 0%
4 | Production Reports | Daily output, efficiency, rejection rate | 2026-07-15 | 2026-08-15 | ⏳ Todo | 0%
4 | Purchasing Reports | PO status, supplier performance, lead time | 2026-08-01 | 2026-08-20 | ⏳ Todo | 0%
4 | QC Reports | Defect trends, batch pass/fail rates, IKEA compliance | 2026-08-15 | 2026-09-05 | ⏳ Todo | 0%
4 | Audit Trail | Full user activity log, change history | 2026-09-01 | 2026-09-15 | ⏳ Todo | 0%
Phase 5 | PHASE 5 — HARDENING & DEPLOY |  |  |  | ⏳ Todo | 0% | Est. Oct 2026–Jan 2027
5 | Performance Optimization | DB indexes, query optimization, caching | 2026-10-01 | 2026-10-20 | ⏳ Todo | 0%
5 | E2E Testing | Playwright tests, API tests, integration | 2026-10-15 | 2026-11-10 | ⏳ Todo | 0%
5 | Docker + CI/CD | Production deploy, staging env, nginx SSL | 2026-11-01 | 2026-11-20 | ⏳ Todo | 0%
5 | User Training | SOP documentation, training materials | 2026-11-15 | 2026-12-10 | ⏳ Todo | 0%
5 | Live Launch | Full production go-live at PT Quty Karunia | 2026-12-15 | 2027-01-15 | ⏳ Todo | 0% | 🎯 Target: Jan 2027

## 📝 Session Log
Session Activity Log — ERP PT Quty Karunia
Session # | Date | Duration (h) | Phase | Module | What was done | Files Changed | Status | Blockers | Next Steps
1 | 2026-01-05 | 4 | 1 | Auth | Setup project, FastAPI base, JWT auth, User model | main.py, users.py, auth.py | ✅ Done |  | RBAC
10 | 2026-01-15 | 5 | 1 | Purchasing | PO KAIN/LABEL types, Dual Trigger TRIGGER 1 | purchasing.py, manufacturing.py | ✅ Done |  | TRIGGER 2
20 | 2026-01-25 | 6 | 1 | BOM | Import dual BOM from Excel, 5845 BOM lines | import_bom_production.py, bom.py | ✅ Done |  | BOM Purchasing
30 | 2026-02-05 | 5 | 1 | Warehouse | Stock opname, WH routes, material receipt | warehouse_endpoints.py | ✅ Done |  | Material debt
40 | 2026-02-15 | 5 | 2 | PPIC | MO list, SPK list, material allocation | ppic.py, MOListPage.tsx | ✅ Done |  | WO creation
50 | 2026-02-25 | 6 | 2 | Purchasing | PO Detail modal, multi-batch WO, qty overflow | PODetailModal.tsx, purchasing.py | ✅ Done |  | PO delete
51 | 2026-03-01 | 7 | 2 | Multi-feat | PO delete/approval, BOM Mgmt page, Masterdata CRUD, 2 MO types | ppic.py, schemas.py, MOListPage.tsx, ... | ✅ Done |  | Daily Input per dept

## 🐛 Bug Tracker
Bug & Issue Tracker — ERP PT Quty Karunia
ID | Found Date | Priority | Type | Module | Description | Root Cause | Status | Fixed Date | Session # | Fix Notes
BUG-001 | 2026-02-20 | 🔴 High | Bug | Masterdata | AdminMasterdataPage duplicate code after file edit | PowerShell truncation issue | ✅ Fixed | 2026-02-20 | 51 | Truncated to line 477
BUG-002 | 2026-02-20 | 🟡 Med | Bug | BOM Mgmt | Unused imports causing linter errors in bom_management.py | Copy-paste leftovers | ✅ Fixed | 2026-02-20 | 51 | Removed Category, ProductType
BUG-003 | 2026-03-01 | 🔴 High | Feature | PPIC | Single MO instead of 2 (BUYER + PRODUCTION) | Old architecture single-MO | ✅ Fixed | 2026-03-02 | 51 | Dual MO trigger implemented
BUG-004 | 2026-03-01 | 🟡 Med | Bug | Navigation | Daily Input generic /daily-production not per dept | Old single-page design | ✅ Fixed | 2026-03-02 | 51 | Per-dept routes + sidebar
BUG-005 | 2026-03-01 | 🔴 High | Bug | App.tsx | Missing routes for 4 dept input pages (Emb/Sew/Fin/Pack) | Never registered | ✅ Fixed | 2026-03-02 | 51 | 4 routes added to App.tsx
BUG-006 | 2026-03-02 | 🟠 Med | Verify | Purchasing | Buttons in PODetailModal may not update status correctly | To be tested | ⏳ Open |  |  | Test Send/Receive/Cancel
BUG-007 | 2026-03-02 | 🟠 Med | Verify | PPIC | MOListPage GET api.ppic.getMOs returns shapes correctly? | API shape unknown | ⏳ Open |  |  | Verify response mapping

## 🎯 Progress Tracker
Session Progress Tracker — ERP PT Quty Karunia (Target: 100–150 Sessions)
Session Range | Phase | Period | Key Deliverables | Sessions Est. | Sessions Done | % Done | Status
1–30 | 1 | Jan 2026 | Auth, Purchasing, BOM, Warehouse, PPIC basics | 30 | 30 | 100% | ✅ Complete
31–50 | 2 | Feb 2026 | Production Form, QC, Rework, Material Debt, Reports draft | 20 | 21 | 100% | ✅ Complete
51–70 | 2 | Mar 2026 | 2 MO types, Daily Input per dept, Fix broken pages/modals, WIP dashboard | 20 | 1 | 5% | 🔵 In Progress
71–90 | 3 | Apr–May 2026 | Material Debt System, WIP Tracking, Kanban, Finish Goods | 20 | 0 | 0% | ⏳ Todo
91–110 | 4 | Jun–Jul 2026 | Analytics Dashboard, Production/Purchasing/QC Reports | 20 | 0 | 0% | ⏳ Todo
111–130 | 5 | Aug–Oct 2026 | Performance tuning, E2E Testing, CI/CD, Docs | 20 | 0 | 0% | ⏳ Todo
131–150 | 5 | Nov 2026–Jan 2027 | User training, pilot run, live launch | 20 | 0 | 0% | ⏳ Todo
📊 OVERALL PROGRESS SUMMARY
Total Sessions Planned |  | ~150
Sessions Completed |  | 51
Overall Progress |  | 34%
Estimated Completion |  | January 2027
Avg Sessions/Week |  | ~5
Critical Path |  | Daily Input + WIP + Reports

## 📅 Weekly Planner
Weekly Development Planner — March 2026 onwards
Week | Date Range | Focus Area | Monday | Tuesday | Wednesday | Thursday | Friday | Weekend/Buffer | Completed?
W1 | Mar 02 – Mar 06, 2026 | Fix broken pages/modals, Daily Input pages | Test & fix PO modal buttons | Test MO list shows 2 MOs | Fix broken sidebar routes | WIP Dashboard | Sewing/Finishing input pages | Review + commit
W2 | Mar 09 – Mar 13, 2026 | Production Daily Input — real data flow | Cutting Input API connect | Embroidery Daily Input | Sewing Daily Input | Finishing Daily Input | Packing Daily Input | Review + commit
W3 | Mar 16 – Mar 20, 2026 | QC Module | QC Inspection form | Defect categories CRUD | Rework workflow UI | QC checkpoint page | QC reports | Review + commit
W4 | Mar 23 – Mar 27, 2026 | Material Debt + WIP | Material debt dashboard | Settlement workflow | WIP transfer logic | WIP dashboard | Integration test | Review + commit
W5 | Mar 30 – Apr 03, 2026 | Performance + Polish | DB query optimization | Pagination on all lists | Loading states fix | Form validation polish | Mobile responsiveness | Review + commit
W6 | Apr 06 – Apr 10, 2026 | Kanban + FG | Kanban board backend | Kanban frontend | FG receipt form | FG stock display | FG dispatch | Review + commit
W7 | Apr 13 – Apr 17, 2026 | Reports Phase 1 | Production daily report | Purchasing summary | QC defect trends | Report export PDF | Dashboard charts | Review + commit
W8 | Apr 20 – Apr 24, 2026 | Reports Phase 2 + Analytics | KPI dashboard | IKEA compliance report | Supplier performance | Week-over-week trends | Export to Excel | Review + commit